## Slide 1
PROJECT PROGRESS REVIEW
ZERO TRUST DIGITAL PROVENANCE PLATFORM
From prototype to
provenance platform
An evidence-led review of delivery, architecture, risk, and the focused path to production readiness.
REGISTER
SIGN
ANCHOR
VERIFY
EXPLAIN
SRS v2.0 • SDS v1.0 • Current implementation
20 SEPTEMBER 2026

## Slide 2
PROGRESS SNAPSHOT
The literal baseline is 74% complete — the working platform is further ahead.
74%
weighted completion across 21 SRS deliverables
12
complete
7
partial / superseded
2
not implemented
The estimate scores complete / partial / absent as 1.0 / 0.5 / 0.0.
Management conclusion
Feature-complete for an advanced academic demonstration after targeted blocker closure; public production approval remains conditional.
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
02

## Slide 3
SCOPE EVOLUTION
Implementation outgrew the original architecture — the formal baseline must catch up.
ORIGINAL SRS / SDS
IMPLEMENTED PLATFORM
CORE API
Python FastAPI orchestrator
CORE API
NestJS 11 domain platform
DATA
SQLite registry and history
DATA
MongoDB collections + transactions
TRUST
ECDSA P-256 embedded in EXIF
TRUST
Ed25519 manifests + signed ledger
AI
EfficientNet-B4 exported to ONNX
AI
ConvNeXt/residual PyTorch service
WEB
React 18 with Vite
WEB
Next.js 15 App Router
Design change
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
03

## Slide 4
IMPLEMENTED CAPABILITY
A complete provenance lifecycle now works in code.
01
Register
hashes, metadata, owner
02
Sign
canonical Ed25519 manifest
03
Anchor
ledger entry + Merkle proof
04
Verify
exact / near match + AI
05
Explain
scores, signals, history
→
→
→
→
Versioned lineage
edits reference parents; revocation preserves history
Developer access
scoped API keys, rotation, usage, and throttling
Operational surface
user and admin dashboards across 27 routes
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
04

## Slide 5
VERIFICATION FLOW
Verification combines provenance, metadata, and AI evidence before it issues a verdict.
01
Upload
validated bytes
held in memory
02
Extract
SHA-256, pHash, EXIF, XMP
→
→
PROVENANCE LANE
exact / pHash match
manifest + ledger recomputation
AI LANE
FastAPI inference
timeout + fallback handling
→
03
Trust
weighted evidence
+ hard caps
→
04
Persist
immutable report
+ policy snapshot
Response
verdict • classification • scores • matched provenance • metadata • signals • signature / ledger checks • processing time
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
05

## Slide 6
DELIVERABLE TRACEABILITY
Backend delivery leads; explainability and formal reporting remain open.
T1 • MODEL
3 complete
3 partial
1 open
ONNX, S1–S6 pack, and cross-generator proof remain partial
T2 • EXPERIENCE
3 complete
3 partial
1 open
GradCAM and PDF reporting are the visible gaps
T3 • PLATFORM
6 complete
1 partial
0 open
Core API, trust, gateway, and Docker are implemented
OPEN
T1.7 GradCAM explainability • T2.7 formatted PDF forensic report
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
06

## Slide 7
ENGINEERING EVIDENCE
The build is healthy; production performance still lacks retained proof.
52
backend tests passed
6
test suites passed
27
frontend page routes
PASS
backend lint • typecheck • frontend lint • production build • AI container health
Accuracy
94.84%
F1
94.79%
ROC-AUC
98.74%
PR-AUC
98.84%
EVIDENCE STILL REQUIRED
p50 / p95 / p99
API, database, ledger, and inference latency on declared hardware
Load + concurrency
throughput, error rate, CPU, memory, recovery behavior
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
07

## Slide 8
AI QUALITY
High validation scores do not guarantee generator robustness.
CHECKPOINT EVIDENCE
94.84%
validation accuracy
98.84%
PR-AUC
KNOWN REGRESSION
0.42%
AI probability for an edited, watermark-removed Gemini image
Three real photographs scored 0.51%, 0.86%, and 1.58% — threshold tuning alone cannot safely separate the sample.
Release gate
generator-held-out evaluation + camera false-positive gate + known-sample regression pack
AI-Service model card • executed regression probe • 20 Sep 2026
08

## Slide 9
PRODUCTION BOUNDARY
Four issues determine whether public production exposure is responsible.
CRITICAL
Unauthenticated role creation
Close POST /roles or enforce super-admin authorization
HIGH
AI cross-generator false negatives
Retrain and enforce held-out promotion gates
HIGH
Performance targets unverified
Publish reproducible latency and load evidence
HIGH
SRS / SDS architecture drift
Issue and approve a current change baseline
NEXT
External C2PA validation • multi-instance ledger leadership • shared rate limits • full E2E suite • PDF reporting
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
09

## Slide 10
COMPLETION ROADMAP
Completion is a three-gate program, not a broad rewrite.
A
Production blockers
protect role mutation
rotate and provision secrets
prove MongoDB transactions
run S1–S7 + load tests
B
AI quality
versioned generator corpus
held-out calibration
known-sample regression
GradCAM or approved replacement
C
Deliverables + governance
formal PDF report
SRS v3.0 / SDS v2.0
dissertation evidence
supervisor sign-off
Gate A secures exposure
Gate B proves model behavior
Gate C closes the academic baseline
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
10

## Slide 11
RECOMMENDED DECISION
Production readiness is achievable after focused closure.
The platform has crossed the prototype threshold. Approval should now depend on seven evidence gates, each with a retained artifact.
G1
Functional
G2
Security
G3
AI quality
G4
Performance
G5
Reliability
G6
Documentation
G7
Deployment
NEXT REVIEW
Approve the revised baseline and verify Gate A evidence before production exposure.
SRS v2.0 • SDS v1.0 • repository evidence • 20 Sep 2026
11