FYP-SP-08  •  FORMAL PROGRESS REVIEW

Zero Trust Digital
Provenance Platform

Concise Project Progress & Deliverables Report

Review focus: What has been delivered, how the implemented system differs from the approved baseline, and what must close before production acceptance.

| Project detail | Value |
| --- | --- |
| Programme | BS Computer Science — Final Year Project |
| Institution | FAST NUCES, Karachi Campus |
| Supervisor | Moheez Ur Raheem |
| Team | Muhammad Shaheer Zafar; Syed Hasham Uddin; Sohaib Sherwani |
| Assessment basis | SRS v2.0, SDS v1.0, FYP-I report, repositories and executed checks |
| Report status | Discussion draft — evidence current to 20 September 2026 |

01

Executive progress snapshot

The platform is substantially implemented, with a small set of high-impact closure items.

| 12 complete deliverables | 7 partial / superseded | 2 not implemented | 74% weighted baseline progress |
| --- | --- | --- | --- |

## Current position

ZTDPP has moved beyond the initial proof of concept into a broad provenance platform. The current system provides secure accounts, API keys, signed and versioned provenance, a hash-chained ledger, perceptual matching, persisted verification reports, administrator tooling, and a separately deployable AI service.

The strongest progress is in provenance lifecycle management, auditability, developer integration, and deployment structure. The remaining work is concentrated in production security closure, AI generalization, formal performance evidence, explainability, and updated SRS/SDS documentation.

Recommended status: Feature-complete for an advanced academic demonstration after targeted blocker closure; not yet approved for unrestricted public production use.

## Decisions required now

1. Approve an updated SRS/SDS baseline that reflects the implemented NestJS, MongoDB, Ed25519, Next.js, ledger, and PyTorch architecture.

2. Treat GradCAM and PDF forensic reporting as explicit pending deliverables, or formally remove/replace them in the approved scope.

3. Hold production promotion until the public role route is secured, the known AI regression is resolved, and retained E2E and performance evidence passes.

02

Scope and architecture evolution

The implementation keeps the project intent while materially changing the technical baseline.

| Area | SRS / SDS baseline | Implemented system | Assessment |
| --- | --- | --- | --- |
| Core API | FastAPI orchestrator | NestJS API; FastAPI dedicated to AI | Broader separation |
| Database | SQLite | MongoDB/Mongoose with transactions | Scalable; docs outdated |
| Signing | ECDSA P-256 embedded in EXIF | Ed25519 signed manifests and ledger receipts | Stronger chain; protocol changed |
| AI | EfficientNet-B4 via ONNX | ConvNeXt Tiny + residual PyTorch service | Superseded design |
| Frontend | React/Vite SPA | Next.js 15 App Router | Broader capability |
| Provenance | Image-embedded manifest | Server-side versioned manifest and lineage | Embedding absent |
| Verdicts | Verified / Unverified / Blocked | Trusted / Likely authentic / Suspicious / Untrusted | Policy expanded |
| Explainability | GradCAM heatmap | No heatmap endpoint or UI | Open requirement |

## Implemented platform shape

Next.js user and administrator dashboards with 27 page routes.

NestJS domain API with authentication, roles, provenance, ledger, reports, settings, and API-key modules.

FastAPI AI service with checkpoint health reporting, image validation, calibrated threshold, and protected prediction endpoint.

Docker Compose and Caddy deployment topology with health checks, limits, TLS routing, and CI workflows.

03

Deliverable register — completed foundation

Direct code, runtime, build, or test evidence supports these outcomes.

| ID | Deliverable | Status | Evidence summary |
| --- | --- | --- | --- |
| T1.1 | Dataset acquisition and preprocessing | Complete | Metadata ingestion, hashing, balanced sampling and split validation. |
| T2.1 | UI/UX and JSON schema | Complete | Production Next.js interface and stable API response conventions. |
| T3.1 | Backend architecture and registry | Complete | NestJS modules and MongoDB entities supersede SQLite. |
| T3.2 | Parallel verification orchestrator | Complete / superseded | NestJS runs local evidence and AI request concurrently. |
| T1.2 | CNN architecture and baseline | Complete | ConvNeXt/residual model and training pipeline are present. |
| T1.3 | Full training and fine-tuning | Complete with limitation | Checkpoint metrics are strong; generalization remains unproven. |
| T3.3 | Crypto verifier and registry | Complete / superseded | Hashes, Ed25519 signatures, ledger links and proofs are recomputed. |
| T2.3 | Frontend component development | Complete / superseded | User and administrator workflows span 27 routes. |
| T3.4 | Trust aggregation and verdict | Complete | Configurable metadata/AI weights, hard caps, signals and four verdicts. |
| T2.6 | Developer dashboard | Complete | API-key create, reveal, rotate, revoke, scope, limits and usage. |
| T3.6 | API gateway middleware | Complete | Hashed keys, scopes, rate limits, usage, headers and Swagger. |
| T3.7 | Docker deployment | Complete | Frontend, API, AI, Caddy, health checks and environment templates. |

04

Deliverable register — remaining work

Seven deliverables need evidence or scope reconciliation; two are absent.

| ID | Deliverable | Status | What remains |
| --- | --- | --- | --- |
| T2.2 | Signer and tamper tests | Partial / superseded | Formalize replacement design and complete tamper evidence pack. |
| T2.4 | Three-verdict conditional rendering | Partial | Document revised verdict model; original blur/block behavior is absent. |
| T1.4 | ONNX export and inference | Partial / superseded | Formally approve PyTorch runtime or provide ONNX artifact. |
| T1.5 | Empirical S1–S6 evaluation | Partial | Run full standardized adversarial suite and retain results. |
| T2.5 | Frontend integration testing | Partial | Add browser E2E coverage for critical user/admin flows. |
| T3.5 | Load tests, latency and dissertation | Partial | Publish reproducible p50/p95/p99 and throughput evidence. |
| T1.6 | Cross-generator fine-tuning | Partial | Resolve known Gemini false negative and prove held-out recall. |
| T1.7 | GradCAM explainability | Not implemented | Implement for ConvNeXt or formally approve a replacement. |
| T2.7 | PDF forensic report | Not implemented | Generate signed/checksum-bound PDF from saved evidence. |

| 12 / 21 complete | 15.5 / 21 weighted points | 73.8% weighted completion |
| --- | --- | --- |

Interpretation: The percentage measures literal delivery against the approved schedule. The implemented platform is broader than the baseline, but changed architecture cannot count as full compliance until the documents are re-baselined.

05

Functional requirement traceability

Eleven SRS use cases mapped to the current workspace.

| Use case | Capability | Status | Conclusion |
| --- | --- | --- | --- |
| UC-01 | Sign image at origin | Partial / superseded | Signed manifests exist; image-embedded signature is absent. |
| UC-02 | Upload for verification | Complete | Validated upload, progress, errors and saved report UI. |
| UC-03 | Parallel verification | Complete / superseded | Hashes/metadata and AI call run concurrently. |
| UC-04 | Cryptographic verification | Complete / superseded | Manifest, signature, ledger and Merkle checks are recomputed. |
| UC-05 | AI anomaly detection | Partial | Service runs; cross-generator false negatives remain. |
| UC-06 | Trust aggregation | Complete | Weighted score, fallback policy, caps, signals and verdicts. |
| UC-07 | Conditional rendering | Partial | Evidence views exist; original blocked-image blur is absent. |
| UC-08 | Manage API keys | Complete | Secure lifecycle, scopes, limits and usage views. |
| UC-09 | External verification API | Complete | Scoped endpoints with rate-limit metadata. |
| UC-10 | History and analytics | Partial | Saved history and JSON export exist; PDF does not. |
| UC-11 | GradCAM heatmap | Not implemented | No computation, response field or visualization. |

Traceability result: Core verification and provenance goals are operational. Literal SRS conformance depends on accepting the revised architecture and closing UC-11 or formally replacing it.

06

How the implemented system works

Operational flow and persistence boundaries.

## Provenance registration

1. Validate an uploaded image or a privacy-preserving content hash and declared source.

2. Compute SHA-256 plus perceptual hashes and normalize available metadata.

3. Create a canonical manifest, sign it with Ed25519, and commit the asset and version in MongoDB.

4. Append a linked ledger entry; edits point to their parent and revocation adds a new signed event.

## Verification and metadata return

1. Process uploaded bytes in memory and extract EXIF, XMP, IPTC, PNG text, C2PA-container presence, SHA-256, pHash and dHash.

2. Call the AI service while searching exact and indexed near-match provenance claims.

3. Recompute signature, manifest, ledger and Merkle evidence instead of trusting stored verdicts.

4. Return scores, effective weights, verdict, signals, matched provenance, input metadata and processing time; persist the complete evidence snapshot.

## Storage boundaries

| Data | Location | Handling |
| --- | --- | --- |
| Accounts, sessions, API keys | MongoDB | Passwords/keys hashed; plaintext API key shown once. |
| Assets, manifests, ledger | MongoDB | Versioned records, signatures, proofs and ownership. |
| Verification reports | MongoDB | Immutable evidence and policy snapshot. |
| Uploaded verification bytes | Memory only | Processed then discarded. |
| AI checkpoint | Read-only model volume | Server-controlled best.pt; excluded from Git. |

07

Quality and production evidence

What has been verified and what still lacks retained proof.

| Check | Result | Evidence |
| --- | --- | --- |
| Backend automated tests | Passed | 52 passed, 10 skipped; 6 suites passed, 1 skipped. |
| Backend lint and typecheck | Passed | ESLint and TypeScript no-emit checks completed. |
| Frontend lint and build | Passed | Lint clean; production build generated static and dynamic routes. |
| AI container and health | Passed | Image built; /health loaded checkpoint and threshold 0.690918. |
| Formal load/latency suite | Pending | No retained benchmark against all SRS targets. |
| Automated browser E2E | Pending | No full S1–S7 cross-service acceptance suite. |

## Security strengths

HTTP-only cookies, refresh-session rotation, password hashing, OTP expiry and revocation.

Peppered API-key hashes, scopes, throttling, CORS allowlists, request IDs and redacted logs.

Upload validation, AI circuit breaker, signing-key history, transactions and hardened containers.

## Production blockers

POST /roles is currently unauthenticated and can affect a privilege boundary.

Production needs durable signing keys, authenticated TLS MongoDB transactions, backup/recovery and fail-closed readiness checks.

Horizontal scale needs a single ledger sealer/leader and a shared rate-limit store such as Redis.

08

AI model status and limitation

Validation metrics are strong; cross-generator reliability is not yet proven.

| 94.84% validation accuracy | 94.79% F1 | 98.74% ROC-AUC | 0.6909 decision threshold |
| --- | --- | --- | --- |

| Evidence | Observed result | Meaning |
| --- | --- | --- |
| Checkpoint | forensic-fusion-b4fbb355522c | Versioned production artifact loads correctly. |
| Edited Gemini image | 0.42% AI probability | Severe false negative on generated content. |
| Three camera photos | 0.51%, 0.86%, 1.58% | Low camera scores; lowering threshold is unsafe. |
| Tiled inference probe | Did not correct miss | Inference reshaping alone is insufficient. |

Model risk: A high aggregate validation score does not establish robustness to unseen generators and post-processing. The UI now reports low output as “No AI pixel signal” and flags evidence/model disagreement, but retraining remains necessary.

## Promotion gate

1. Build a versioned corpus across Gemini/Imagen, DALL-E, Midjourney, Flux, Firefly, Stable Diffusion, camera images and post-processing variants.

2. Use generator-held-out splits and calibrate only on validation data.

3. Require per-generator recall, camera false-positive, calibration and known-regression gates before promotion.

09

Priority gap and risk register

Risks ranked by effect on security, acceptance, and trustworthy operation.

| ID | Priority | Risk | Required treatment |
| --- | --- | --- | --- |
| R1 | Critical | Unauthenticated role creation | Remove public route or require JWT plus super-admin; add regression test. |
| R2 | High | AI cross-generator false negatives | Retrain; enforce generator-held-out promotion tests. |
| R3 | High | SRS/SDS architecture drift | Issue approved SRS/SDS revision and change log. |
| R4 | High | GradCAM absent | Implement for ConvNeXt or formally approve replacement. |
| R5 | High | Performance targets unverified | Publish reproducible latency, throughput and resource report. |
| R6 | Medium | PDF report absent | Generate checksum-bound PDF from immutable snapshot. |
| R7 | Medium | External C2PA validation absent | Integrate conforming verifier and trust-store policy. |
| R8 | Medium | Distributed operations unproven | Use leader/single sealer and Redis-backed limiting. |
| R9 | Medium | Full E2E suite absent | Automate S1–S7, auth, revocation, ambiguity and outage cases. |

Risk concentration: R1 must close before any public exposure. R2–R5 determine whether the product can claim reliable, explainable, requirements-aligned production performance.

10

Completion roadmap

Work sequenced by production risk and acceptance value.

## Phase A — production blockers

1. Protect/remove public role creation and audit every mutation route.

2. Rotate development credentials; provision durable signing keys and recovery procedures.

3. Deploy authenticated TLS MongoDB replica set and execute readiness/migration checks.

4. Complete S1–S7 plus browser/API E2E automation.

5. Run load and latency benchmarks with p50/p95/p99, throughput, errors, CPU and memory.

## Phase B — AI quality and explainability

1. Create the cross-generator, camera and post-processing evaluation corpus.

2. Retrain and calibrate with generator-held-out evaluation and regression gates.

3. Implement GradCAM for ConvNeXt or approve and document a replacement explanation method.

## Phase C — deliverables and governance

1. Generate the formal PDF forensic report from the immutable verification snapshot.

2. Publish SRS v3.0 and SDS v2.0 for the actual architecture and security boundaries.

3. Update the dissertation with implementation, model, adversarial and performance evidence.

4. Complete final traceability review and supervisor sign-off.

Suggested review order: Approve the revised baseline first, then use the acceptance gates on the final page as the definition of done.

11

Acceptance gates and final assessment

A concise definition of done for project completion and production readiness.

| Gate | Required evidence | Exit criterion |
| --- | --- | --- |
| G1 Functional | Automated S1–S7 plus critical user/admin flows | All critical paths pass |
| G2 Security | Route audit, secret/dependency/container scans | No unresolved critical/high finding |
| G3 AI quality | Held-out matrices, per-source recall, camera FPR | Approved metrics; regression passes |
| G4 Performance | Reproducible p50/p95/p99 and throughput | Targets pass or are formally revised |
| G5 Reliability | DB/AI/key/restart/ledger recovery tests | Graceful degradation; no corrupt records |
| G6 Documentation | Approved SRS/SDS, runbook, API guide, model card | Documents match deployment |
| G7 Deployment | TLS staging, backups, probes, monitoring, rollback | Repeatable deployment and rollback |

## Final assessment

ZTDPP is no longer an early prototype. It is a coherent, security-aware provenance platform whose implemented capability is broader than the original FYP-I design. Its strongest areas are provenance lifecycle management, ledger evidence, API-key integration, persisted trust reporting, and the user/administrator experience.

The path to completion is clear and finite: close the privilege route, re-baseline the documentation, prove performance and end-to-end behavior, improve AI generalization, and resolve GradCAM and PDF reporting. These items should be treated as acceptance gates.

Discussion conclusion: Proceed with targeted closure work. Do not describe the current build as unrestricted production-ready until G1–G7 are evidenced and approved.

Evidence basis: SRS v2.0; SDS v1.0; FYP-I report; frontend commit 6f3b816; backend commit 927fd63; architecture and production-readiness guides; AI model card; executed build, lint, typecheck, unit-test and container-health checks.